## JIRA Backlog
Issue ID | Issue Type | Summary | Description | Priority | Story Points | Assignee | Sprint
LT-1 | Epic | User Interface Development | Design and implement web UI for translator | High | 13 | Aman Sharma | Sprint 1
LT-2 | Story | Create Text Input Form | User can enter English text | High | 5 | Priya Singh | Sprint 1
LT-3 | Story | Language Selection Dropdown | User selects source and target languages | High | 5 | Rohit Verma | Sprint 1
LT-4 | Story | Translate Button Action | Trigger translation on click | High | 3 | Neha Gupta | Sprint 1
LT-5 | Epic | Backend Development | Develop server logic using Flask | High | 13 | Vikram Patel | Sprint 2
LT-6 | Story | Integrate Transformer Model | Load MarianMT model | High | 8 | Anjali Mehta | Sprint 2
LT-7 | Story | API Endpoint for Translation | POST endpoint to process text | High | 5 | Aman Sharma | Sprint 2
LT-8 | Story | Error Handling | Handle invalid input and server errors | Medium | 3 | Priya Singh | Sprint 2
LT-9 | Epic | Testing | Ensure system reliability | Medium | 8 | Rohit Verma | Sprint 3
LT-10 | Story | Unit Testing | Test backend functions | Medium | 5 | Neha Gupta | Sprint 3
LT-11 | Story | Integration Testing | Test UI + Backend workflow | Medium | 5 | Vikram Patel | Sprint 3
LT-12 | Story | Performance Testing | Measure response time | Low | 3 | Anjali Mehta | Sprint 3
LT-13 | Epic | Deployment | Deploy app to cloud | Medium | 8 | Aman Sharma | Sprint 4
LT-14 | Story | Prepare Production Environment | Configure server and dependencies | Medium | 5 | Priya Singh | Sprint 4
LT-15 | Story | Deploy Web Application | Deploy to hosting platform | Medium | 5 | Rohit Verma | Sprint 4
LT-16 | Story | Post-Deployment Validation | Verify live functionality | Low | 3 | Neha Gupta | Sprint 4